## Sheet1
Task | Subtask | Start Date | End Date
Literature Review |  | 2024-01-11 | 2024-02-07
| Review economics and VAR | 2024-01-11 | 2024-01-25
| Review sentimenet analysis | 2024-01-25 | 2024-02-06
Collect Data
| Identify sources | Completed
| Within the data calculate the proportion at which France is mentioned by Francaphone countries and vice versa | 2024-01-11 | 2024-01-20
| Build Corpus | 2024-01-11
Develop Sentiment Analysis Program
| Write and test code on sample data | Completed
| Vector Auto Regression | 2024-02-07 | 2024-02-14
| test code and adjust on entire corpus | 2024-03-01 | 2024-03-10
Write Report | Write literature review and method | 2024-02-08 | 2024-02-24
| Write Results and Conclusion | 2024-03-10 | 2024-04-01
Prepare Presentation
|  | 2024-03-04 | 2024-03-10